## Sheet1
ID	Risk	Probability	Impact	Ownership	Mitigation
Roof
Roof.1	RBK/FH access to the roof for regular roof maintenance	Low	Low	RBK	Follow RBK H&S policies
Roof.2	KCE access to the roof for panel maintenance	Low	Low	KCE	Programme works outside of term time where possible. On the irregular occasions that KCE will require access to the roof (expected to be once every 2 – 4 years), KCE will ensure that RBK H&S policies are followed at all times. KCE will ensure that the solar panel installation is serviced and maintained as required by the manufacturer.
Roof.3	Unplanned roof maintenance, such as a roof leak	Low	High	KCE/RBK	Following a written request from RBK acting reasonably and where such works cannot be carried out without their removal KCE will temporarily remove the Solar Panels and any relevant Equipment from the Building or the roof of the Building as soon as reasonably practicable and at KCE's expense so as to allow RBK to carry out such works including of repair and maintenance to the Building or its roof as cannot be reasonably undertaken without such removal
Roof.4	Roof damage during installation of the panels	Low	Medium	KCE	KCE will indemnify RBK against all damage made to the building caused by the installation of the panels by: conducting the installation according to an agreed method between KCE, RBK and the installer. Once commenced ensuring that the works are completed as soon as is practicable. Undertaking the works in a good workmanlike manner using good quality materials. Contractually obligating the installer to make good any damage made to the building during the works and to ensure that the installer maintains professional indemnity insurance of one million pounds.
	Emergency access to the roof	Very Low	Medium	RBK/KCE	In the unlikely event that an emergency arises in conjunction with the solar panels, RBK will notify KCE immediately to enable the situation to be resolved. KCE will require access to the roof to address the issue.
Roof.5	Defect on the premises	Low	Medium	RBK	In the event that an existing defect on the premises is noted as a result of the work of KCE (during installation or maintenance) KCE will notify RBK immediately
Roof.6	Change in roof ownership	Low	Medium	KCE/RBK	An agreement between RBK and KCE will be drawn up regarding ownership and access to the roof. In any transfer of ownership of the school RBK will ensure KCE's ability to use the roof as planned if at all reasonably possible.
PV panels
Panel.1	Panel performance - lower amount of electricity generated than predicted	Low	Medium	KCE	KCE will select proven reliable panels, with long warranty period. Typical digression of panel performance over time has been allowed for in the financial modelling
Panel.2	Vandals destroy the PV system	Low	High	KCE	KCE contract with shareholders will cover this risk. KCE will have insurance to cover this.
Panel.3	System performance - failure of PV system	Low	High	KCE	KCE will choose proven reliable panels, with long warranty period. Allowance for regular maintenance and replacement of inverters to ensure that the system perfoms well
Panel.4	Overshadowing	Low	High	KCE	There are no currently known or expected plans for building on the south of the site. Only a substantial/high building would pose a risk of overshadowing
Panel.5	Unforseen issue affecting panel performance	Low	Medium	KCE	If an unforseen issue arises that might affect the panel performance, RBK/the school will contact KCE immediately to advise that the issue has arisen.
Panel.6	Distribution Network Operator refusing, or being very slow regarding G59 connection	Low	Low	KCE	Early negotiations with the DNO.
Installation
Install.1	Working at height	High	Medium	KCE/RBK	KCE will contract with a reputable installer with a strong health and safety record. Installer will be contractually required to produce a written method statement and risk assessment for all of their work.
Install.2	Working at a school	High	Medium	KCE/RBK	The installer shall be contractually required to follow RBK H&S policies for school sites including generation of risk assessments and method plans as appropriate. Either the installer will provide only CRB screened staff to work on site, or KCE will provide constant supervision.
Install.3	Health, safety and environment risks during construction	High	Medium	KCE/RBK	KCE will use a reliable and competent installer. Installer will be contractually required to provide HSE policies and procedures for this specific site. KCE will act as client under the CDM (2007) regulations. Installer will be contractually required to follow RBK H&S policies. All HS&E documentation and procedures will be freely available to RBK to review.
Install.4	Availability of installer within the time frame	Medium	Medium	KCE	KCE will work closely with the installer to plan the works appropriately, and to try to work outside of term time where possible
Install.5	Contract delivery	Medium	Medium	KCE/RBK	KCE will use model contracts to ensure that the installer will deliver the lump sum contract to our desired standards and specification

Team
Team.1	Track record and reliability of KCE	Low	Medium	KCE	TTK has a strong record in local projects. Our team has installed solar PV at King Athelstan primary and we have a combination of technical, financial and business experience to achieve this project.
Team.2	Safeguarding children	Low	High	KCE	KCE undertakes to ensure that all of its staff, agents and/or contractors who may be from time to time on the Property or the Building (if any) work to the standards set out in the DCSF publication and guidance ‘Safeguarding Children and Safer Recruitment in Education’ (2007) or any similar government guidance replacing the same and any local standards set by RBK or the school.
Team.3	Disputes with adjoining owners	Low	Low	KCE	If any disputes arise between KCE and any adjoining owners about the solar panel installation. KCE will abide by RBK's decision.
Team.4	Disputes between the parties	Low	Low	KCE/RBK	KCE will adopt an open book approach with the school and with RBK. Any disputes that arise between KCE and RBK will be settled in good faith through mediation. A procedure will be developed.
Political
Pol.1	Change in FITs	Low	High	KCE	The FiT scheme now seems to have stabilised and is unlikley to have any more upsets that would affect this scheme in 2013
Planning
Plan.1	Change in planning laws	Low	Medium	KCE	KCE will work, as far as possible, within GDPOs to eliminate the need for planning consent (e.g. Panels stay beneath current roof line, 5m from edge of curtilage, and 1m from any roof edge). KCE will check for further covenants or restrictions; input from RBK would be appreciated
Finance
Fin.1	Panel performance lower than predicted	Low	Medium	KCE	KCE will choose proven reliable panels, with long warranty period. Typical digression of panel performance over time has been allowed for in the financial modelling
Fin.2	Poor weather - less electricity generated than predicted	Low	Low	KCE	PV panels still perform in poor solar conditions. KCE to use actual data from installed panels to ensure that minimum panel performance has been allowed for. Ongoing monitoring of panel performance will enable KCE to build up a database of local PV panel performance for Kingston solar conditions.
Fin.3	Negotiation with FiT payment supplier	Low	Low	KCE	KCE will begin the process early to minimise the impace of delays. Shareholders are not repayed until year 3 to allow time to build up a cashflow reserve and to allow for negotiations at the start of the FiT contract.
Fin.4	Objections from school's existig supplier regarding FiT payments	Low	Low	KCE	KCE will include the existing supplier in the FiT negotiations
Fin.5	Late FIT payment	Medium	Medium	KCE	KCE will only pay interest to shareholders when the accounts are in surplus.
Fin.6	Shareholders wanting their money back	Medium	Medium	KCE	Allowance for trading between shareholders to alleviate pressure KCE to return money. Return capital alongside interest repayments
Fin.7	Ability of the school to pay for electricity	Low	Medium	KCE/RBK	Only applicable if KCE charge for the electricity, if so it will only be at a rate lower than the market rate so it will be a cost saving to the school
Other
Misc.1	Force Majeure; weather, political or environmental event that disrupts the project	Low	High	KCE	Whilst the risk cannot be planned, KCE will have insurance to cover force majeure events.